## Schedule
| Phase 2 Detailed Schedule | [8 empty] | Revision 5 | 2012-05-09
2012 |  | Schedule by Task | [5 empty] | Detailed Schedule and Activities
Week | Beginning | Task 7 | Task 8 | Task 9 | Task 10 | Task 11 | Task 12 | Step | Technical Analysis Activity | Report Development | Meetings (notes 1 and 2) | Dates (note 3)
- | Pre-Work | [6 empty] | 1 to 7 | SSC defines 3 scenarios, Establish TOTF, PAs develop initial scope for TOTF, Possible TOTF Webex, PAs develop consistent process for generation units not represented, PAs develop "less than peak" definition, PAs define reliability test to be performed in Task 8
1 | 2012-01-02 | [7 empty] | Finalize "Go" Decision (NETL) PA team organizes
2 | 2012-01-09 | [6 empty] | 8 |  |  | TOTF - organize, review scenarios, schedule, and work product, discussion of transmission alternatives | 1/10-11/12
3 | 2012-01-16 | [6 empty] | 9 to 11 | PAs set locations for new and idled gen based on SSC spec by NEEM region
4 | 2012-01-23 | [6 empty] | 9 to 11 | Share generation locations with TOTF, request feedback |  |  | TOTF Conf Call 1/26
5 | 2012-01-30 | [6 empty] | 9 to 11 | PAs develop data sets for each scenario, provide to TOTF
6 | 2012-02-06 | [6 empty] | 9 to 11 | PA Gap Analysis |  |  | TOTF Conf Call 2/9
7 | 2012-02-13 | [6 empty] | 9 to 11
8 | 2012-02-20 | [6 empty] | 12 |  |  | TOTF - Review of data sets, Joint Working Session on modeling and gap analysis results | Feb 22-23
9 | 2012-02-27 | [6 empty] | 9 to 11, 13 | PAs identify new transmission for each scenario
10 | 2012-03-05 | [6 empty] | 10, 11, 13
11 | 2012-03-12 | [6 empty] | 10, 11, 13 |  |  |  | Totf Conf Call 3/15
12 | 2012-03-19 | [6 empty] | 10, 11, 13 |  |  | EIPC team working session
13 | 2012-03-26 | [6 empty] | 14 |  |  | TOTF - Review/feedback on cases, discuss alternatives, Joint Working Session on results | March 28-29
14 | 2012-04-02 | [6 empty] | 10, 11, 13 | PAs refine solutions, consider additional alternatives, and test transfers |  | (Easter week)
15 | 2012-04-09 | [6 empty] | 10, 11, 13 |  |  | EISPC Meeting - Atlanta EIPC team working session | April 10-11 TOTF Conf Call 4/12
16 | 2012-04-16 | [6 empty] | 15 | PAs incorporate SSC and TOTF feedback |  | SSC / TOTF - Omaha Presentation on status, discussion, and early input on preliminary results | April 18-19
17 | 2012-04-23 | [6 empty] | 11, 13, 16 |  |  |  | TOTF Conf Call 4/26
18 | 2012-04-30 | [6 empty] | 11, 13, 16 |  |  | EIPC team working session | Possible TOTF Conf Call 5/3
19 | 2012-05-07 | [6 empty] | 11, 13, 16
20 | 2012-05-14 | [6 empty] | 17 |  |  | TOTF - Memphis Review and feedback on revised cases | May 15-16
21 | 2012-05-21 | [6 empty] | 13, 18 | PAs complete transfer tests
22 | 2012-05-28 | [6 empty] | 13,18 |  |  | EISPC Meeting | May 31-June1 TOTF Conf Call 5/31
23 | 2012-06-04 | [6 empty] | 13,19 | Share results with TOTF and SSC
24 | 2012-06-11 | [6 empty] | 13, 20 to 28 | PAs perform reliability check on Scenario A
25 | 2012-06-18 | [6 empty] | 13, 20 to 28 | bar: Schedule by Task Task 7 to Schedule by Task Task 8
26 | 2012-06-25 | [6 empty] | 13, 20 to 28 | PAs determine reliability adjustments to Scenario A | bar: Schedule by Task Task 7 to Schedule by Task Task 8
37 | 2012-07-02 | [6 empty] | 20 to 28 | PAs perform reliability check on Scenario B |  | (July 4th on Wednesday) | bar: Schedule by Task Task 7 to Schedule by Task Task 8; Schedule by Task Task 10
38 | 2012-07-09 | [6 empty] | 20 to 28 | Start production cost analyses | bar: Schedule by Task Task 8 to Schedule by Task Task 10
39 | 2012-07-16 | [6 empty] | 20 to 28 | PAs determine reliability adjustments to Scenario B | bar: Schedule by Task Task 8 to Schedule by Task Task 10
30 | 2012-07-23 | [6 empty] | 20 to 28 | PAs perform reliability check on Scenario C, start prod cost and cost est on Scenario B | bar: Schedule by Task Task 8 to Schedule by Task Task 10
31 | 2012-07-30 | [6 empty] | 20 to 28, 35 |  | Report Outline Available | bar: Schedule by Task Task 8 to Schedule by Task Task 11
32 | 2012-08-06 | [6 empty] | 20 to 28 | PAs determine reliability adjustments to Scenario C | bar: Schedule by Task Task 8 to Schedule by Task Task 11
33 | 2012-08-13 | [6 empty] | 20 to 28 | PAs start prod cost and cost est on Scenario C | bar: Schedule by Task Task 9 to Schedule by Task Task 11
34 | 2012-08-20 | [6 empty] | 20 to 28 | bar: Schedule by Task Task 9 to Schedule by Task Task 11
35 | 2012-08-27 | [6 empty] | 28,31, 32 |  | Draft of Task 7 & Task 8 Sections | bar: Schedule by Task Task 9 to Schedule by Task Task 11
36 | 2012-09-03 | [6 empty] | 28, 31, 32 |  |  | EISPC Meeting | September 6-7 | bar: Schedule by Task Task 9 to Schedule by Task Task 12
37 | 2012-09-10 | [6 empty] | 29, 31-33, 37 |  |  | SSC/TOTF - Detroit Scenario Results and Draft Report sections on Task 7 and Task 8 | September 20-21 | bar: Schedule by Task Task 9 to Schedule by Task Task 12
38 | 2012-09-17 | [6 empty] | 31 to 33 |  |  | (Rosh Hashana is on Monday 9/17) | bar: Schedule by Task Task 9 to Schedule by Task Task 12
39 | 2012-09-24 | [6 empty] | 30 | Production Cost Work Finished | SSC Written Input on Draft (1) | (Yom Kippur is on Wednesday 9/29) | bar: Schedule by Task Task 9 to Schedule by Task Task 12
40 | 2012-10-01 | [6 empty] | 34 | G&T Cost Estimates Finished | bar: Schedule by Task Task 10 to Schedule by Task Task 12
41 | 2012-10-08 | [6 empty] | 36 |  | Production Cost Section | bar: Schedule by Task Task 11 to Schedule by Task Task 12
42 | 2012-10-15 | [6 empty] | 36 |  | G&T Cost Section | EISPC Meeting | October 18-19 | bar: Schedule by Task Task 11 to Schedule by Task Task 12
43 | 2012-10-22 | [6 empty] | 40 |  | SSC Written Input on Draft (2) | bar: Schedule by Task Task 11 to Schedule by Task Task 12
44 | 2012-10-29 | [6 empty] | 38 |  | Revised Report | bar: Schedule by Task Task 11 to Schedule by Task Task 12
45 | 2012-11-05 | bar: Schedule by Task Task 12
46 | 2012-11-12 | [6 empty] | 39, 40 |  | SSC Written Input on Draft (3) | bar: Schedule by Task Task 12
47 | 2012-11-19 | [9 empty] | (Thanksgiving is on 11-22) | bar: Schedule by Task Task 12
48 | 2012-11-26 | [6 empty] | 41 |  | Final Draft for Last Review | EISPC Meeting | November 29-30 | bar: Schedule by Task Task 12
49 | 2012-12-03 | [6 empty] | 42 |  |  | SSC - Final Review (4) and Project Wrap-up | December 4-5 | bar: Schedule by Task Task 12
50 | 2012-12-10 | [6 empty] | 40 |  | Final SSC Comments Due | (Hanukkah is on Sunday 12/9) | bar: Schedule by Task Task 12
51 | 2012-12-17 | [6 empty] | 43 | bar: Schedule by Task Task 12
52 | 2012-12-24 | [6 empty] | 44 | Report Final |  | (Christmas Day is on Tuesday 12/25) | bar: Schedule by Task Task 12
53 | 2012-12-31
Notes:
| (1) | Schedule by Task Task 7: SSC - Conference calls/Webex between meetings (3) |  |  |  | Meeting dates shown in green are fixed
|  | Schedule by Task Task 7: TOTF - Bi-weekly conference calls through September (15) |  |  |  | Meeting dates shown in light purple can be moved with the week or before or after to resolve other conflicts
| (2) | Schedule by Task Task 7: For TOTF, members must have obtained CEII clearance.
| (3) | Schedule by Task Task 7: All meetings shown as 2 days. Length of meetings to be determined based on agenda and time required.
| Issues: | Schedule by Task Task 7: Specific meeting dates and length of meetings TBD
Meeting locations - common for TOTF?
Current Week

## Task 7 & 8 Detail
Task 7 – Develop a solved load flow case for each Scenario |  |  |  | Green Bars |  |  |  | Task 8 – Perform reliability testing on each load flow and adjust as necessary | [7 empty] | Maroon Bars
Current schedule dates: 1/9/12 to 6/15/12 | [7 empty] | Current Schedule dates: 6/11/12 to 8/10/12
| Activity | Week Starting -> | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04 | 2012-06-11 | 2012-06-18 | 2012-06-25 | 2012-07-02 | 2012-07-09 | 2012-07-16 | 2012-07-23 | 2012-07-30 | 2012-08-06
Scenario 1 (B1&B13)
Pass 0 - complete
Pass 1 - complete
Pass 2 - 4/5/12 | bar: 2012-04-09
Pass 3 - 4/30/12 for discussion at TOTF mtg | bar: 2012-04-09 to 2012-04-23
TOTF meeting - 5/15-16/12 (already scheduled) | bar: 2012-05-14
Pass 4 - following TOTF meeting |  |  | 2012-05-14: 2012-05-18
Pass 5 - final case for SSC/TOTF review (post) |  |  | 2012-06-04: 2012-06-08
SSC/TOTF Webinar |  |  | 2012-06-11: 2012-06-13
Task 8 – start 6/18/12 | bar: 2012-06-18
Any adjustments needed due 6/29/12 | bar: 2012-06-18 to 2012-06-25
Determine Flowgates | bar: 2012-06-25
Re-run final testing 7/6/12 | bar: 2012-07-02
Production cost work starts 7/9/12 |  |  | 2012-07-09: 2012-07-09
Scenario 2 (B1&B13)
Pass 0 - initial case for PA review |  |  | 2012-04-16: 2012-04-19
Pass 1 - after PA internal review (post) |  |  | 2012-05-14: 2012-05-14
TOTF meeting – 5/15-16/12 (already scheduled) | bar: 2012-05-14
Pass 2 - case for discussion at TOTF meeting (post) |  |  | 2012-06-04: 2012-06-08
TOTF meeting – tentative | bar: 2012-06-11
Pass 3 - after further PA work (post) |  |  | 2012-06-18: 2012-06-20
Pass 4 - final case for SSC/TOTF review (post) |  |  | 2012-07-02: 2012-07-06
SSC/TOTF Webinar |  |  | 2012-07-09: 2012-07-11
Task 8 – start 7/16/12 | bar: 2012-07-16
Any adjustments needed due 7/27/12 | bar: 2012-07-16 to 2012-07-23
Determine Flowgates | bar: 2012-07-23
Re-run final testing 8/3/12 | bar: 2012-07-30
Production cost work starts 8/6/12 |  |  | 2012-08-06: 2012-08-06
Scenario 3 (B1)
Pass 0 - complete
Pass 1 - 4/30/12 for discussion at TOTF mtg | bar: 2012-04-09 to 2012-04-23
TOTF meeting – 5/15-16/12 (already scheduled) | bar: 2012-05-14
Pass 2 - following TOTF meeting |  |  | 2012-05-14: 2012-05-18
Pass 3 - after further PA work (post) |  |  | 2012-06-04: 2012-06-08
Pass 4 - final case for SSC/TOTF review (post) |  |  | 2012-06-18: 2012-06-20
SSC/TOTF Webinar |  |  | 2012-06-25: 2012-06-27
Task 8 – start 7/2/12 | bar: 2012-07-02
Any adjustments needed due 7/13/12 | bar: 2012-07-02 to 2012-07-09
Determine Flowgates | bar: 2012-07-09
Re-run final testing 7/20/12 | bar: 2012-07-16
Production cost work starts 7/23/12 |  |  | 2012-07-23: 2012-07-23

## Revision History
Revision | Date | Description of Changes Made and Reason for Change
0 | 2012-12-06 | Final schedule established during pre-work.
1 | 2012-01-03 | Change TOTF conference call dates to Thursdays in accordance with TF agreement.
2 | 2012-01-13 | Correct dates of meetings and conference calls.
3 | 2012-03-23 | Show progress to date in week and beginning date columns by shading gray, add Current Week marker, show additional weeks for steps 10 and 11.
4 | 2012-04-06 | Add Task 7 Detail tab.
5 | 2012-05-09 | Revise detailed dates on Task 7 and Task 8 Tab.