## Sheet1
| Phase 2 Detailed Schedule | [9 empty] | 2011-08-19
2012 |  | Schedule by Task | [5 empty] | Detailed Schedule and Activities
Week | Beginning | Task 7 | Task 8 | Task 9 | Task 10 | Task 11 | Task 12 |  | Technical Analysis Activity | Report Development | Meetings (notes 1 and 2) | Dates (note 3)
- | Pre-Work | [7 empty] | SSC defines 3 scenarios, Establish TOTF, PAs develop initial scope for TOTF, Possible TOTF Webex, PAs develop consistent process for generation units not represented, PAs develop "less than peak" definition, PAs define reliability test to be performed in Task 8
1 | 2012-01-02 | [7 empty] | Finalize "Go" Decision (NETL) PA team organizes
2 | 2012-01-09 | [9 empty] | TOTF - organize, review scenarios, schedule, and work product, discussion of transmission alternatives | 2 days
3 | 2012-01-16 | [7 empty] | PAs set locations for new and idled gen based on SSC spec by NEEM region
4 | 2012-01-23 | [7 empty] | Share generation locations with TOTF, request feedback
5 | 2012-01-30 | [7 empty] | PAs develop data sets for each scenario, provide to TOTF
6 | 2012-02-06 | [7 empty] | PA Gap Analysis
| 2/9-10/12 | [9 empty] | EISPC Meeting -- Washington DC (following NARUC Winter Meetings) | 2 days
7 | 2012-02-13
8 | 2012-02-20 | [9 empty] | TOTF - Review of data sets, Joint Working Session on modeling and gap analysis results | 2 days
9 | 2012-02-27 | [7 empty] | PAs identify new transmission for each scenario
10 | 2012-03-05
11 | 2012-03-12 | [9 empty] | EIPC team working session | 2 days
12 | 2012-03-19
13 | 2012-03-26 | [9 empty] | TOTF - Review/feedback on cases, discuss alternatives, Joint Working Session on results | 2 days
| 3/29-31/12 | [9 empty] | Potential EISPC Meeting--OR--early next week | 2 days
14 | 2012-04-02 | [7 empty] | PAs refine solutions, consider additional alternatives, and test transfers |  | (Easter week)
| 4/3-4/12 | [9 empty] | Potential EISPC Meeting -- the week before the SSC meeting but early in the week (Easter Week) | 2 days
15 | 2012-04-09 | [9 empty] | SSC - TOTF Presentation on status, discussion, and early input on preliminary results | 2 days
16 | 2012-04-16 | [7 empty] | PAs incorporate SSC and TOTF feedback
17 | 2012-04-23
| 4/26-27/12 | [9 empty] | Potential EISPC Meeting | 2 days
18 | 2012-04-30 | [9 empty] | EIPC team working session | 2 days
19 | 2012-05-07
20 | 2012-05-14 | [9 empty] | TOTF - Review and feedback on revised cases | 2 days
21 | 2012-05-21 | [7 empty] | PAs complete transfer tests
22 | 2012-05-28 | [9 empty] | Memorial Day 5/28)
23 | 2012-06-04 | [7 empty] | Share results with TOTF and SSC
| 6/7-8/12 | [9 empty] | Potential EISPC Meeting | 2 days
24 | 2012-06-11 | [7 empty] | PAs perform reliability check on Scenario A | bar: Schedule by Task Task 7 to Schedule by Task Task 8
25 | 2012-06-18 | bar: Schedule by Task Task 8
26 | 2012-06-25 | [7 empty] | PAs determine reliability adjustments to Scenario A | bar: Schedule by Task Task 8
| 6/28-29/12 | [9 empty] | Potential EISPC Meeting (may not be needed) | 2 days | bar: Schedule by Task Task 8
37 | 2012-07-02 | [7 empty] | PAs perform reliability check on Scenario B, start prod cost and cost est on Scenario A |  | (July 4th on Wednesday) | bar: Schedule by Task Task 8 to Schedule by Task Task 10
38 | 2012-07-09 | bar: Schedule by Task Task 8 to Schedule by Task Task 10
39 | 2012-07-16 | [7 empty] | PAs determine reliability adjustments to Scenario B | bar: Schedule by Task Task 8 to Schedule by Task Task 10
30 | 2012-07-23 | [7 empty] | PAs perform reliability check on Scenario C, start prod cost and cost est on Scenario B | bar: Schedule by Task Task 8 to Schedule by Task Task 10
31 | 2012-07-30 | [8 empty] | Report Outline Available | bar: Schedule by Task Task 8 to Schedule by Task Task 11
| 8/2-3/12 | [9 empty] | Potential EISPC Meeting (Note: NARUC Summer Meetings are the week before in Portland, OR) | 2 days | bar: Schedule by Task Task 8 to Schedule by Task Task 11
32 | 2012-08-06 | [7 empty] | PAs determine reliability adjustments to Scenario C | bar: Schedule by Task Task 8 to Schedule by Task Task 11
33 | 2012-08-13 | [7 empty] | PAs start prod cost and cost est on Scenario C | bar: Schedule by Task Task 9 to Schedule by Task Task 11
34 | 2012-08-20 | bar: Schedule by Task Task 9 to Schedule by Task Task 11
35 | 2012-08-27 | [8 empty] | Draft of Task 7 & Task 8 Sections | bar: Schedule by Task Task 9 to Schedule by Task Task 11
36 | 2012-09-03 | [9 empty] | (Labor Day is on Monday 9/3) | bar: Schedule by Task Task 9 to Schedule by Task Task 12
| 9/6-7/12 | [9 empty] | Potential EISPC Meeting--OR--early next week | 2 days | bar: Schedule by Task Task 9 to Schedule by Task Task 12
| 9/10-11/12 | [9 empty] | Potential EISPC Meeting -- the week of the SSC Meeting but before the SSC Meeting | 2 days | bar: Schedule by Task Task 9 to Schedule by Task Task 12
37 | 2012-09-10 | [9 empty] | SSC/TOTF - Scenario Results and Draft Report sections on Task 7 and Task 8 | 2 days | bar: Schedule by Task Task 9 to Schedule by Task Task 12
38 | 2012-09-17 | [9 empty] | (Rosh Hashana is on Monday 9/17) | bar: Schedule by Task Task 9 to Schedule by Task Task 12
39 | 2012-09-24 | [7 empty] | Production Cost Work Finished | SSC Written Input on Draft (1) | (Yom Kippur is on Wednesday 9/29) | bar: Schedule by Task Task 9 to Schedule by Task Task 12
40 | 2012-10-01 | [7 empty] | G&T Cost Estimates Finished | bar: Schedule by Task Task 10 to Schedule by Task Task 12
41 | 2012-10-08 | [8 empty] | Production Cost Section | bar: Schedule by Task Task 11 to Schedule by Task Task 12
| 10/11-12/12 | [9 empty] | Potential EISPC Meeting | 2 days | bar: Schedule by Task Task 11 to Schedule by Task Task 12
42 | 2012-10-15 | [8 empty] | G&T Cost Section | bar: Schedule by Task Task 11 to Schedule by Task Task 12
43 | 2012-10-22 | [8 empty] | SSC Written Input on Draft (2) | bar: Schedule by Task Task 11 to Schedule by Task Task 12
44 | 2012-10-29 | [8 empty] | Revised Report | bar: Schedule by Task Task 11 to Schedule by Task Task 12
45 | 2012-11-05 | bar: Schedule by Task Task 11 to Schedule by Task Task 12
46 | 2012-11-12 | [8 empty] | SSC Written Input on Draft (3) | bar: Schedule by Task Task 11 to Schedule by Task Task 12
47 | 2012-11-19 | [9 empty] | (Thanksgiving is on 11-22) | bar: Schedule by Task Task 12
48 | 2012-11-26 | [8 empty] | Final Draft for Last Review | bar: Schedule by Task Task 12
| 11/29-30/12 | [9 empty] | Potential EISPC Meeting (Note: NARUC Winter Meetings on 11/11-14 but there would not be sufficient time to review Draft 3 for final review.) | 2 days | bar: Schedule by Task Task 12
49 | 2012-12-03 | [9 empty] | SSC - Final Review (4) and Project Wrap-up | 2 days | bar: Schedule by Task Task 12
50 | 2012-12-10 | [8 empty] | Final SSC Comments Due | (Hanukkah is on Sunday 12/9) | bar: Schedule by Task Task 12
| 12/13-14/12 | [9 empty] | Potential EISPC Meeting (if needed for final report review/comments) | 2 days | bar: Schedule by Task Task 12
51 | 2012-12-17 | bar: Schedule by Task Task 12
52 | 2012-12-24 | [7 empty] | Report Final | bar: Schedule by Task Task 12
53 | 2012-12-31
Notes:
| (1) | Schedule by Task Task 7: SSC - Conference calls/Webex between meetings (3) |  |  |  | Meeting dates shown in green should not be moved from the week indicated
|  | Schedule by Task Task 7: TOTF - Bi-weekly conference calls through September (15) |  |  |  | Meeting dates shown in light purple can be moved to the week before or after to resolve other conflicts
| (2) | Schedule by Task Task 7: For TOTF, members must have obtained CEII clearance.
| (3) | Schedule by Task Task 7: All meetings shown as 2 days. Length of meetings to be determined based on agenda and time required.
| Issues: | Schedule by Task Task 7: Specific meeting dates and length of meetings TBD
Meeting locations - common for TOTF?